## Mobilisation GANTT
2025-11-07
High Med Consortium - Mobilisation Plan for Isleworth (Lot 1) |  | PROJECT TIMESCALES | Start Date: | 2026-03-24 | End Date: | 2027-03-31 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26
TASK |  | Critical Success Factor | Owner | Start | Complete by | Completed | time axis 2026-03-24 to 2026-07-26
 | time axis 2026-03-24 to 2026-07-26
[7 empty] | WEEK 1 | [5 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18
1.0 CONTRACTS
1.1 | Notification of Outcome |  | COMMISSIONER | 2026-02-20 | 2026-02-20
1.2 | Close of Standstill |  | COMMISSIONER | 2026-03-06 | 2026-03-06
1.3 | Contract Award |  | COMMISSIONER | 2026-03-06 | 2026-03-06
1.4 | Contract Due Diligence |  | US | 2026-03-06 | 2026-03-24
1.5 | Budgets agreed |  | US | 2026-03-06 | 2026-03-24
1.6 | Contract Completion | 1 | SM/GS | 2026-03-24 | 2026-03-24
2.0 STAKEHOLDER ENGAGEMENT & COMMUNICATIONS
2.1 | Confirm Communications & Engagement Plan |  | SS | 2026-03-27 | 2026-03-27
2.2 | Notifications and update access details: PCSE PCSE Supplies CQRS Immform |  | MK | 2026-03-30 | 2026-03-30
2.3 | Stakeholder Engagement & Meetings. Including: - NWL ICB - London Borough of Houslow (Landlord) - Brentwood PCN, Neighbourhood Practices, Community Health and Social Care Providers - Patients and Service Users - LMC - CQC - VCSEs including Age UK Hounslow, HFEH Mind, Cultivate London, Ealing & Hounslow Community Voluntary Service (EHCVS), and Carers UK Hounslow. |  | SM/SS | 2026-03-31 | Ongoing
2.4 | Invite Patients into PPG meetings to meet the team and address/discuss any concerns |  | MK | 2026-04-06 | 2026-04-08
2.5 | New website and telephone messaging development. Including: website information to patients on new services and new staff practice team, patient information, incorporating SystmOne, Docman, AccuRx, HSCN connectivity, TeamNet, NHS App, PATCHS, and Ardens functionality. |  | MK | 2026-04-06 | 2026-04-08
2.6 | Create Patient Information Leaflet and telephone messaging |  | MK | 2026-04-08 | 2026-04-08
2.7 | Press Release, Social Media & PR Campaigns to: - Patients and Public via local press - Community Groups - Schools and Children's centres - Practices & Primary Care (GMP, surestart, social services, health centre) - Secondary Care Providers - Wider Health & Social Care |  | SS | 2026-04-09 | 2026-04-10
3.0 PATIENT ENGAGEMENT AND CONSULTATION
3.1 | Draft consultation brief; outlining patient concerns identified, outline of current services problems and constraints, aims to provide solution, and possible options. This will include; covering experience and accessibility to inform and reaffirm service design, including which days of the week to provide extended opening until 8pm. |  | SS | 2026-04-13 | 2026-04-17
3.2 | Engage stakeholder feedback on briefing, including; patients, NHSE, NWL ICB, and Healthwatch |  | SS | 2026-04-20 | 2026-04-22
3.3 | Collate feedback and opinions via surveys, PPG, practice, waiting area and community events |  | MK | 2026-04-23 | 2026-04-24
3.4 | Issue Consultation report with feedback and proposed actions, inviting further feedback | 2 | MK | 2026-04-24 | 2026-04-24
3.5 | Update action implementation plan, including scheduling stakeholder reviews, and ‘You said, We Did’ |  | SS | 2026-04-27 | 2026-04-28
3.6 | Open Day |  | SM | 2026-07-15 | 2026-07-15
3.7 | Update and disseminate Consultation brief |  | MK | 2026-07-20 | 2026-07-24
4.0 GOVERNANCE
4.1 | Finalise integrated governance arrangements |  | SM/GS | 2026-03-25 | 2026-03-27
4.2 | CQC Statement of Purpose Review and notification of change of Provider |  | GS | 2026-03-30 | 2026-03-31
4.3 | Comprehensive review of Health Inequalities |  | SS | 2026-03-30 | 2026-04-10
4.4 | Update KPI and contract reporting and verify test data, confirming roles for Governance/Performance Leads, including: - CQC - QOF - Enhanced Primary Care Services - Referrals |  | MK | 2026-04-13 | 2026-04-15
4.5 | Set-up of Governance Group inc terms of reference and 1st meeting |  | SM/GS | 2026-04-16 | 2026-04-17
4.6 | Update Clinical Governance Manual and related procedures, including incidents management, and complaints. |  | SM | 2026-04-20 | 2026-04-24
4.7 | Work with Brentwood PCN and ICB forums to progress and update agreed consistent patient comms, pathways, and working arrangements |  | SM/GS | 2026-04-27 | Ongoing
4.8 | Complete assurance process relating to Policy alignment to ICB |  | SM | 2026-04-30 | 2026-05-01
4.9 | Make all relevant policies available to staff for service commencement e.g. risk management, prescribing etc. and highlight any changes to practice which may be required |  | MK | 2026-05-04 | 2026-05-08
4.10 | Ensure that all staff have read practice’s Clinical Governance Manual and are fully compliant with the protocol therein |  | MK | 2026-05-15 | 2026-05-15
4.11 | Staff training on any changes |  | FN/SM | 2026-06-15 | 2026-06-19
4.12 | Test local referral pathways /PRISM |  | MK | 2026-06-22 | 2026-06-23
4.13 | Prescription set up including (but not limited to): Prescribing email sent to Neelam Bose Prescription Security Management and handover records Prescription processing process set up and monitor |  | MK | 2026-06-22 | 2026-06-23
4.14 | Clinical handover, to include: Safeguarding Children and Adults Homeless Palliative Care High risk drugs Asylum seekers Cancer register Nursing Homes/ Care Homes Emergency Drugs Emergency equipment's Control drugs on premises Vaccination in the fridge Death Certificate Register |  | SM | 2026-06-22 | 2026-06-26
5.0 WORKFORCE & TRAINING
5.1 | Complete Operational Model; workforce deployment and clinic scheduling |  | FN | 2025-10-01 | 2025-10-31 | 2025-04-30
5.2 | Identify and agree GPs to deploy to the contract. |  | SM/US | 2025-10-27 | 2025-10-31 | 2025-04-30
5.3 | Confirm TUPE Implications. |  | FN | 2026-03-25 | 2026-03-27
5.4 | Request ELI/TUPE Information |  | FN | 2026-03-27 | 2026-03-27
5.5 | Arrange Meetings to Introduce High Med Medical Centre |  | FN | 2026-03-30 | 2026-04-10
5.6 | Consultation Period |  | FN | 2026-04-13 | 2026-05-11
5.7 | Confirm those to be transferred |  | FN | 2026-05-12 | 2026-05-15
5.8 | Reconfirm staff deployment and recruit vacancies or any posts that have become vacant, including external recruitment campaign |  | MK | 2026-05-18 | 2026-05-18
5.9 | TUPE Completion | 3 | FN | 2026-06-15 | 2026-06-19
5.10 | Conduct Training Needs Analysis |  | MK | 2026-06-22 | 2026-06-23
5.11 | Update and confirm Employee contracts |  | MK | 2026-06-23 | 2026-06-23
5.12 | Confirm complete Workforce in place for service commencement, including implementation of management | 4 | MK | 2026-06-24 | 2026-06-24
5.13 | Confirm and assign responsibilities and Lead Roles |  | MK | 2026-06-25 | 2026-06-26
5.14 | Deliver any Training Identified, including training for all on new Practice working arrangements, Equipment & IM&T, pathway, policies |  | SM/MK | 2026-06-25 | 2026-07-10
6.0 PREMISES
6.1 | Complete Due Diligence including further site visit and discussions with London Borough of Houslow (Landlord) |  | FN | 2026-03-30 | 2026-04-03
6.2 | Complete and sign initial rental agreement and update insurances |  | FN | 2026-04-03 | 2026-04-03
6.3 | Complete Premises Audit, including: - Accessibility - Privacy - Health & Safety Assessment - Fire Reg Cert - Legionnaires Testing/water checks - Asbestos survey - PAT testing - Oxygen and equipment - Energy usage - DDA Assessment |  | MK | 2026-04-06 | 2026-04-10
6.4 | Liaise with London Borough of Houslow (Landlord) and make arrangements for any reparations |  | MK | 2026-04-09 | 2026-04-10
6.5 | Finalise and Sign Property Lease including FM and Maintenance service agreements | 5 | FN/US | 2026-04-10 | 2026-04-10
7.0 EQUIPMENT & SYSTEMS
7.1 | Confirm and reconcile Asset List and any equipment included with contract. |  | SN | 2026-03-30 | 2026-04-03
7.2 | Confirm ICT strategy and plans; including optimisation of digital services, incorporating SystmOne, HSCN connectivity, TeamNet, Docman, AccuRx, NHS App, and Ardens. |  | US | 2026-04-06 | 2026-04-10
7.3 | Review and update DSP Action Plan |  | SN | 2026-04-13 | 2026-04-14
7.4 | Liaise with NWL/Incumbent to complete Data Discovery and records transfer plan |  | SN | 2026-04-14 | 2026-04-17
7.5 | Purchase/lease new equipment where required. Including setup of telephone system. |  | US/SN | 2026-04-20 | 2026-05-01
7.6 | Complete DPIA with NWL ICB and Incumbent |  | SN | 2026-04-30 | 2026-05-01
7.7 | Update local Business Continuity & Disaster Recovery Plan |  | MK | 2026-05-04 | 2026-05-05
7.8 | Test secure records transfer |  | SN | 2026-05-07 | 2026-05-08
7.9 | FINAL secure records transfer |  | SN | 2026-05-25 | 2026-05-29
7.10 | Records Validation |  | SN | 2026-06-01 | 2026-06-12
7.11 | Test all equipment |  | SN | 2026-06-15 | 2026-06-19
7.12 | Sign-off and Final Assurance of records transfer | 6 | SN | 2026-06-19 | 2026-06-19
7.13 | Staff training/updates in the use of new equipment & systems |  | SN | 2026-06-22 | 2026-06-23
7.14 | Smartcard access for High Med Partners, GPs and Operational team EMIS Web access, TeamNet, AccuRx, and Docman set-up. |  | SN | 2026-06-23 | 2026-06-24
8.0 OPERATIONAL MANAGEMENT
8.1 | Emergency Equipment and Drugs Vaccinations/Immunisation Stock |  | MK | 2026-04-13 | 2026-04-14
8.2 | New signage with Doctors information |  | MK | 2026-06-15 | 2026-06-19
8.3 | Schedule rotas including (but not limited to): Duty Doctor GPs, other clinicians Nurses/HCA Reception Teams Administration Teams |  | MK | 2026-06-22 | 2026-06-23
8.4 | Operational Readiness Test |  | MK | 2026-06-23 | 2026-06-26
8.5 | Go Live |  | MK | 2026-07-01 | 2026-07-01
9.0 PROGRESS UPDATE AND SERVICE REVIEW
9.1 | Weekly Mobilisation Review (internal) |  | SM/US/MK | 2026-03-24 | 2026-07-31
9.2 | SMT monthly performance meeting |  | SM/US/MK | 2026-05-01 | 2026-07-31
9.3 | Commissioner validate Business as usual | 7 | US | 2026-07-10 | 2026-07-10
CORE MOBILISATION TEAM
SM | Dr Shumaila Mahmood | Partner & Clinical Director
GS | Dr Gursharan Singh | Partner & Quality & Safety Lead
US | Dr Usama Safeer | Finance & Mobilisation Lead
SS | Dr Saira Safeer | Admin and Public Health Lead
FN | Dr F Nasir | HR & Training Lead
MK | Ms Manjot Kaur | Service Delivery & Operations Lead
SN | Mr Safeer Nasir | IT & Digital Lead
CRITICAL SUCCESS FACTORS
1 | Contract Completion
2 | Issue Consultation report with feedback and proposed actions, inviting further feedback
3 | TUPE Completion
4 | Confirm complete Workforce in place for service commencement, including implementation of management
5 | Finalise and Sign Property Lease including FM and Maintenance service agreements
6 | Sign-off and Final Assurance of records transfer
7 | Commissioner validate Business as usual